## Guide (hidden)
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Project Title
User Story | Story Point(s) | Priority
As a voter, I want to be able to answer to questions | 5 | 5 | Medium | High | Low
As a voter, I want to be able to read results. | 10 | 5
As a voter, I want to be able to read questions. | 5 | 5 | 3 | 5 | 1
As a voter, I want to be able to see the instructions so i know how to use the machine | 2 | 1
As a voter, I want to be able to browse candidates | 3 | 3
As a voter, I want to be able to browse by party | 3 | 2
As a voter, I want to be edit my answers to questions | 7 | 3
As a voter, I want to be able to go back and forth between the questions | 10 | 3
As an admin, I need to be able to edit the questions | 6 | 2
As an admin, I need to be able to delete the questions | 5 | 5
As an admin, I need to be able to add the questions | 5 | 5
As an admin, I need to be able to login | 5 | 4
As a voter, I want to be able to see candidates answers | 4 | 4

## sprint_backlog_sprint1 (2)
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a voter, I want to be able to answer to questions | 5 | Juho | Done
Task: HTML |  | Juho |  | 0 | 1 | 0 | 0 | 0
Task: JSP |  | Juho |  | 0 | 0 | 1 | 1 | 2
Task: Cookies |  | Juho |  | 0 | 0 | 1 | 4 | 2
Task: merge everything into master and clean |  | Juho |  | 0 | 0 | 0 | 0 | 2
As a voter, I want to be able to read questions. | 5 | Juho | Done
Task: Making SQL database |  | Juho |  | 1 | 0 | 0 | 0 | 0
Task: Making Connections to the database |  | Juho |  | 0 | 1 | 1 | 0 | 0
Task: Printing questions from the database |  | Juho |  | 0 | 0 | 2 | 0 | 0
As an admin, I need to be able to login | 6 | Muhammed | Done
Task: Creating SQL database |  | Muhammed |  | 1 | 0 | 0 | 0 | 0
Task: Connections to the database |  | Muhammed |  | 0 | 1 | 1 | 0 | 0
Task: MD5 crypting |  | Muhammed |  | 0 | 0 | 0 | 1 | 0
Task: Checking user credentials and login |  | Muhammed |  | 0 | 1 | 1 | 1 | 0
As an admin, I need to be able to delete the questions | 5 | Matias | Done
Task: Make connections to mysql |  | Matias |  | 1 | 1 | 0 | 0 | 0
Task: Show questions in admin page |  | Matias |  | 0 | 2 | 0 | 0 | 0
Task:Ability to delete |  | Matias |  | 0 | 1 | 0 | 0 | 0
Task:UI |  | Matias |  | 0 | 1 | 0 | 0 | 0.5
As an admin, I need to be able to add the questions | 5 | Matias | Done
Task: Make connections to mysql |  | Matias |  | 0 | 0 | 1 | 0 | 0
Task:Ability to add |  | Matias |  | 0 | 0 | 1 | 0 | 0
Task:UI |  | Matias |  | 0 | 0 | 1 | 0 | 0.5
As an admin, I need to be able to edit the questions | 5 | Matias | Done
Task: Make connections to mysql |  | Matias |  | 0 | 0 | 0 | 1 | 0
Task:Ability to edit |  | Matias |  | 0 | 0 | 0 | 2 | 0
Task:UI |  | Matias |  | 0 | 0 | 0 | 1 | 0.5
As a voter, I want to be able to browse candidates | 3 | Muhammed | Done
Task: Make connections to mysql |  | Muhammed |  | 0 | 0 | 0 | 0 | 1
Task: Modify Dao and create new JSP for candidates |  | Muhammed |  | 0 | 0 | 0 | 0 | 2
Task: Print all candidates from database |  | Muhammed |  | 0 | 0 | 0 | 0 | 1
TOTAL |  |  |  | 3 | 9 | 10 | 11 | 11.5

## sprint2
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a voter, I want to be able to read results. | 10 | Matias | Done
Task: Make the score system |  |  |  | 0 | 3 | 2 | 0 | 0
Task: Rank and sort canditates |  |  |  | 0 | 0 | 3 | 0 | 0
Task: Compare users and canditates answes |  |  |  | 3 | 0 | 0 | 0 | 0
Task: Show the results |  |  |  | 0 | 0 | 0 | 3 | 0
As a voter, I want to be able to browse by party | 3 | Muhammed | Done
Task: Make JSP and java for browsing parties |  |  |  | 0 | 2 | 1 | 0 | 0
Task: Connection to database |  |  |  | 1 | 0 | 0 | 0 | 0
Task: Move candidates under partiy categories |  |  |  | 0 | 0 | 1 | 2 | 0
Task: Statements for parties to show correct candidates |  |  |  | 0 | 0 | 0 | 2 | 1
As a voter, I want to be able to see candidates answers | 4 | Juho | Done
Task: Making "readAllAnswers" class to Dao |  |  |  | 2 | 0 | 0 | 0 | 0
Task: making the .Java file |  |  |  | 1 | 0 | 1 | 2 | 1
Task: making the .jsp file |  |  |  | 2 | 1 | 0 | 2 | 1
TOTAL |  |  |  | 9 | 6 | 8 | 11 | 3

## sprint_planning_meetings
Sprint Planning | Participants
Week 13 | Matias Mäkelä | Muhammed Al-Zahu | Juho Glumov
Online | Online | Online | Online | If present mark X
2022-03-28 | X | X | X
Week 14
Location | Online | Online | Online
2022-04-04 | X | X | X
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/